## Sheet1
Change Request ID | Description | Risks | Actions
change_request_1 | The client should have direct access to his/her only one account where he can view a history of previous transactions. | 1-SRS_ View Account _002 2-SRS_ View Account _003 3-SRS_ View Account _004 4-ViewClient_wireFrame_1 5-Low_Design_ViewAccountsList_Client_1 6-Low_Design_addAccount_client_1 7- change code in view client class. 8- classDiagram_viewAccount_Client_001 9- change client login sequence diagram 10- change frontend task 11- update Add New Account in SRS. | 1- update SRS 2- update DDD 3- update client login sequence diagram 4-update view client class diagram 5- change view Account frontend 6- change view client class 7- tasks will be assigned on Trello.
change_request_2 | Team member change | 1-Future tasks assignation (NONE) 2--Running tasks assignation (NONE) 3-Training needed for the new member 4-Training required from the old member (NONE) | 1- The new member is required to read the SRS to understand the application's features, also she needs to check the running application. Then the tasks will be assigned to her. -Expected time (2 hrs).